## Sheet1
TASKS | ASSIGNED TEAM MEMBERS | REVIEW DATE | DUE DATE | PROGRESS STATUS | COMMENT
Finalize & update MVP user flow (student + transport provider Agent screen) in Figma | Jace | 8/28/2025 | 8/31/2025 | 100% | Completed
Share updated flow with Design + Dev teams | Jace | 8/28/2025 | 8/31/2025 | 100% | Completed
Outline impactful activities that Studexpress Ambassadors can leverage to effectively promote the Studexpress brand. | Itunuoluwa and Olapoju Teniola Israel | 8/28/2025 | 8/31/2025 | 100% | Completed
Competitor Deep Dive – Study transport & student-focused apps in Nigeria (e.g., GUO, God Is Good Motors, Shuttlers, Max.ng). Document their strengths, weaknesses, and gaps StudExpress can exploit. | Preciousteenet and Ohe-G | 8/28/2025 | 8/31/2025 | 100% | Completed
Set up official social media accounts (FB) Create & post 2 awareness contents (transport providers) | Son of RIGHT-HAND | 8/28/2025 | 8/31/2025 | 100% | Completed
Design StudExpress Web View UI (consistent with MVP mobile style) Design Registration, Onboarding & Home Screen | Omoba, A_Deal Design and Brownson Micheal | 8/28/2025 | 8/31/2025 | 5% | Pending
Mobile App Development: Build Registration, Signup, Login Onboarding & Home Screen for the student side | Destiny | 8/28/2025 | 8/31/2025 | 100% | Completed
Backend Development: Build Authentication and registration for the student flow | Edet | 8/28/2025 | 8/31/2025 | 100% | Completed
Mobile app Design: Create empty screens for student, agent and transport providers design the rate trip screen arrange flow and update authentication and registration flow, link student profile to agent flow, and finalize all the mobile app design | Jace | 2025-09-11 | 2025-09-25 | 100% | Completed
Create and post 3 awerness contents on Studexpress FB account | Son of RIGHT-HAND | 2025-09-11 | 2025-09-25 | 0% | Pending
Mobile App Development: Build Registration , Signup, Login Onboarding, Company Info, Driver Info and the verification of driver identity screens for the Transport provider flow, | Destiny | 11/02/2025 | 11/09/2025 | 70% | Pending
Backend Development: Build Authentication and registration and also the different api for handling transport provider role e.g private car owner or transport company, storing company info and driver info for the Transport provider flow | Edet | 2025-09-11 | 2025-09-25 | 100% | Completed
Backend development: Build api to fetch tranport provider data in the dashboard | Edet | 11/02/2025 | 11/09/2025 | 0% | Pending
Backend development: Build api to add new trip and new driver | Edet | 11/02/2025 | 11/09/2025 | 0% | Pending
Backend development: Build api to handle editing of driver and trips | Edet | 11/02/2025 | 11/09/2025 | 0% | Pending
Backend development: Build api to fetch trips and drivers | Edet | 11/02/2025 | 11/09/2025 | 0% | Pending
Backend development: Build api to handle removal of driver and cancellation of trip | Edet | 11/02/2025 | 11/09/2025 | 0% | Pending
|  | 11/02/2025 | 11/09/2025
Web Design: Design pages for registration, authentication and onboarding of students, transport provider and agents, landing page, booking,payment, profile, and bookings detail page | Jace | 11/02/2025 | 11/09/2025 | 55% | Pending
Web Design: Design mobile view screens from web ui ( registration, verification , and signup screens) | A_Deal Design | 11/02/2025 | 11/09/2025 | 0% | Pending
|  | 11/02/2025 | 11/09/2025
Mobile App Development: Build transport provider dashboard screen and add trip screen. | Destiny | 11/02/2025 | 11/09/2025 | 50% | Pending
Mobile App Development: Build add driver, edit driver and edit trip screen for transport providers. | Destiny | 11/02/2025 | 11/09/2025 | 50% | Pending
Mobile App Development: Build trip management and notification screen for transport providers. | Destiny | 11/02/2025 | 11/09/2025 | 50% | Pending
Mobile App Development: Build cashout and profile screen for transport providers | Destiny | 11/02/2025 | 11/09/2025 | 50% | Pending
Web Development: Build the landing page and student signup page | Gideon | 11/02/2025 | 11/09/2025 | 0% | Pending