## TASK SHEET
MODULES | TASKS | USER INTERFACE | ASSIGNED TEAM MEMBER | PROGRESS STATUS | DATE ASSIGNED | DATE DUE | DATE UPDATED | COMMENT
POST UTME APPLICATION | Allow student sitting for olevel to be displayed on the olevel verification payment invoice. This means to move the olevel upload form ahead of the olevel verification payment in order to validate the sittings and display on the invoice. | STUDENTS | MICHAEL | Open | 2025-10-08 | 2025-11-08
STUDENT DATA MANAGEMENT | Add message to specify file format and file size limit for student passport on post utme application form and student bio-data update form | STUDENTS | MICHAEL | Open | 2025-10-08 | 2025-11-08
POST UTME APPLICATION | Ensure that applicant's application number will remain their jamb reg no instead of generating an application number after applying for post utme | STUDENTS | MICHAEL | Open | 2025-10-08 | 2025-11-08
POST UTME APPLICATION | Remove the application number from the application successful page after applying for post utme | STUDENTS | BRUNO | Open | 2025-10-08 | 2025-11-08
HOMEPAGE | Remove FUTMinna from the home page | STUDENTS | JOBA | Open | 2025-10-08 | 2025-11-08
COURSE REGISTRATION MANAGEMENT | Include school name and logo in course form printout. Header should be the same used in the school's general documents as sent | STUDENTS | DESTINY | Open | 2025-10-08 | 2025-12-08
COURSE REGISTRATION MANAGEMENT | Add student passport to the course form | STUDENTS | DESTINY | Open | 2025-10-08 | 2025-12-08
EXAMINATION MANAGEMENT | Add passport to examination docket. | STUDENTS | BRUNO | Open | 2025-10-08 | 2025-12-08
EXAMINATION MANAGEMENT | Get template of examination docket | STUDENTS | MR MAYOWA | Open | 2025-10-08 | 2025-12-08
PAYMENTS MANAGEMENT | Create a receipt printing portal that will take the student username and the type of payment they need receipts for, and also allow receipt generating links for the students on applicant and student ports. | STUDENTS | MICHAEL/BRUNO | Open | 2025-10-08 | 13/8/2025
EXAMINATION MANAGEMENT | Reimplement examination docket to suit the template received | STUDENTS | MICHAEL/BRUNO | Open | 2025-10-08 | 13/8/2025
HOSTEL MANAGEMENT | Fix the hostel dashboard data updating | STAFFS | MICHAEL | Open | 2025-10-08 | 13/8/2025
EXAMINATION RESULT MANAGEMENT | Enable students to generate transcripts at final year phase. This transcript layout will depend on the template we receive from the institution | STUDENTS | MICHAEL/DESTINY | Open | 2025-10-08 | 14/8/2025
REPORT GENERATION | Fix the printing alignment issues on all pages for invoices | ADMINISTRATOR | MICHAEL | Open | 2025-10-08 | 14/8/2025
EMAIL MANAGEMENT | Fix and ensure all email communication with students to all actions on the application | STUDENTS | MICHAEL | Open | 2025-10-08 | 15/8/2025
EXAMINATION RESULT MANAGEMENT | Reimplement the examination processing to handle UNIBEN processing methods | ADMINISTRATOR | MICHAEL | Open | 2025-10-08 | 17/8/2025
EXAMINATION RESULT MANAGEMENT | Fix the result summary template | ADMINISTRATOR | MICHAEL | Open | 2025-10-08 | 17/8/2025
DATA FILTERING | Fix all the filters on the application and ensure they're working | ADMINISTRATOR | MICHAEL | Open | 2025-10-08 | 17/8/2025
EXAMINATION RESULT MANAGEMENT | Generate raw score template for UNIBEN | ADMINISTRATOR | MICHAEL | Open | 2025-10-08 | 18/8/2025
EXAMINATION RESULT MANAGEMENT | Generate senate approval list template for UNIBEN | ADMINISTRATOR | MICHAEL | Open | 2025-10-08 | 19/8/2025

## KEYS
Open | MICHAEL | ADMINISTRATOR
25% | JOBA | LECTURER
50% | MICHAEL/ JOBA | STUDENTS
75% | MICHAEL/BRUNO | STAFFS
Closed | MICHAEL/DESTINY | ACADEMIC BOARD
BRUNO
DESTINY
ESTHER
MICHAEL/DESTINY/JOBA
MR MAYOWA